## Sheet1
Ashleworth Parish Council Risk Register May 2021
Reviewed May 2021
Assessment scoring: 1 = low. 2 = low/medium. 3 = medium. 4= medium / high. 5 = high.
Activity | Risk | Cause | Effect | Likelihood | Severity | Actions
1. Finances | Sudden large expenditure required or excessive under budgeting | Unforeseenproblem/poor budgeting | Service not provided. Lack of confidence in Council. Inability to carry out functions. Insufficient funds for contingencies. | 2 | 3 | Council has some reserves Insurance in place to cover major risks
2. Finances | Fraud | Inadequate controls | Loss of funds | 1 | 5 | Annual internal and external audit Bank balances reported to every meeting. Bank balances and expenditure audited by councillor at every meeting. Cheques signed by 2 Councillors. Internal Financial Check conducted twice a year. Insurance in place to cover any resulting financial losses.
3. Contractors | Contractors not supplying agreed services | Unavailable due to illness, poor weather | Poor services | 2 | 4 | Maintain an up to date register of assets Regular maintenance arrangements for physical assets Annual review of risk and adequacy of insurance cover
4. Parish Council records and archives | Loss of Parish Council records and archives | Fire, flood, theft | No records found | 2 | 4 | Lodge archived records on website as well as hard copies. Backup data.
5. Records | Loss of documents on Clerk's computer | Computer crash, fire, flood, theft | Loss of records, agreed actions | 2 | 4 | Back-up copies of documents onto portable hard drive and store away from PC Minutes kept as hard copies and copied to all councillors
6. Clerk to the Parish Council | Unavailability | Resignation, illness etc | Work of the Parish Council cannot be carried out | 2 | 5 | Urgent work carried out by the Chairman and other Parish Councillors. Contact the GAPTC about availability of temporary cover
7. PC meetings | Accommodation unavailable for meetings | Damage to village hall | Meeting room unavailable | 1 | 2 | Use nearby village hall or similar amenity
8. Membership of Parish Council | Vacancies in membership | Resignation, retirement, insufficient nominations at elections | Meetings cannot take place due to be being inquorate | 2 | 5 | Identify, on an unofficial basis, local residents who might be interested in becoming members of the Parish Council. Advertise on local noticeboards and public meeting areas in parish when necessary
9. Assets | Damage | Vandalism, Accident, storm | High cost of repair Loss of Assets Disruption Damage to public property or person | 2 | 4 | Insurance cover Maintain an up to date register of assets Regular maintenance arrangements for physical assets Annual review of risk and adequacy of insurance cover
10. Minutes | Inaccurate reporting of Council business in the Minutes | Confusion and misunderstandings. Actions not reflecting intentions of Council | Claim against Council | 2 | 5 | Approval by Council Chairman to sign copies of minutes
11. Activities | Damage to third party individual due to service or amenity provided | Poor maintenance. Accident | Claim against Council | 2 | 4 | Public Liability Insurance Regular checks of facilities.Ensure all amenities/facilities are maintained to appropriate level.